## Bill
Sr. No. | Bill No | Bill Date | Value | GST | Bill with GST | Vehicle No | Structure Weight | Receiving | Remarks | Plant
1 | LEC/23-24/0100 | 2023-04-13 | 32356 | 3882.72 | 36238.72 | SAFEXPRESS | 354 |  | Foundation bolts plates | Plant Finalised value | 13715000
2 | [9 empty] | GST @ 12% | 1645800
3 | [9 empty] | Total plant value with GST | 15360800
4
5 | [9 empty] | Erection
6 | [9 empty] | Plant Erection value | 1085000
7 | [9 empty] | GST @ 18% | 195300
8 | [9 empty] | Total plant value with GST | 1280300
9
10 | [9 empty] | Total Value of plant with Erection | 16641100
11
12 | [9 empty] | Amount Received
13 | [9 empty] | Receiving Date | Amount
14 | [9 empty] | 2023-04-03 | 500000
|  |  | 32356 |  | 36238.72 |  | 354
[10 empty] | Total payment received | 500000

## Payment schedule
Payment schedule (Dated 14-04-2023)
Description | Material Value | GST % | GST Value | Total Billing
Plant (Machines +Electrical) Finalized Value | 13715000 | 12 | 1645800 | 15360800
Erection Value | 1085000 | 18 | 195300 | 1280300
Total Value with GST |  |  |  | 16641100
Material Dispatched till now with GST |  |  |  | 36239
Advance Received till now |  |  |  | 500000
Advance payment request |  |  |  | 3000000
Payment request by …… for 1st lot dispatch |  |  |  | 4000000
Payment request by …… for 2nd lot dispatch |  |  |  | 3500000
Payment request by …… for 3rd lot dispatch |  |  |  | 3000000
Payment Request before …….for Electrical material dispatch |  |  |  | 2341100
After 1 month of commissioning or 500MT of production whichever is earlier with post dated Cheques. |  |  |  | 300000
16641100
0
Payment terms as per agreement

## Bill detail
1st structure
Total Finalised Structure | 24000Kg
Machine | 13646250
Total | 13646250
P& F Value | 113116.5093
Total for machine With P& F | 13759366.5093
Machinery Value after Discount | 11491799.4474
Structure | 24000
Structure Value | 2640000
P& F Value | 21883.4907
Total With P& F | 2661883.4907
Structure value after discount | 2223200.5526
Total Value with Machine & Structure | 13715000
GST @12% | 1645800
Total Value with GST | 15360800

## rough working
16421250 | 1600000
13715000 | 975000
2706250 | 200000
0.1648 | 2775000
0.8352 | 2317675.2683 | 2595796.3005 | Electrical material value for dispatch