## project details
LARK ENGINEERING CO. (INDIA) PVT. LTD.
SALES WORK ORDER
Sales Order No. |  |  | LP -102 |  |  |  | Target Dispatch Start |  |  |  | 01-06-2021.
Enquiry No. |  |  | LP -2207-8/10/2020 |  |  |  | Erection Start |  |  |  | 2021-07-01
Enquiry Date/ Order Finalization Date |  |  | 1-06-2019/29-10-2020 |  |  |  | Commisioning |  |  |  | 2021-09-01
Client |  |  | M/s Kuldeep Poultry Pvt. Ltd |  |  |  | Category |  |  |  | 8-10 TPH with 8 Bins
|  |  | Mr. Kuldeep |  |  |  | M/s Kuldeep Poultry Pvt. Ltd, dabwali, haryana, Email: Kuldeeppoultrydab@gmail.com, Mob: +91-9888089150
Contact No. |  |  | Mobile: +91-9888089150
Other concern person/ Designation | [6 empty] | Best Way to reach Site --
Contact No. | [6 empty] | Sales Person ( In contact ) - Harjot singh/Rajan syal
Email ID's |  |  | kuldeeppoultrydab@gmail.com
Site condition at the time of finalization | [6 empty] | Layout status ( Primary / Final )--------Final
Bare Ground | [6 empty] | Approved (Y/N)
Shed work started | [6 empty] | Submitted On
Existing Shed | [6 empty] | Layout Rev. No.
Approximate Formulation ( Broiler / Layer / Cattle / Other ) …………………..Broiler
| Ingredients |  | percantage |  | Ingredients |  |  | percantage |  | Ingredients |  |  | percantage
1. maize |  |  |  |  | 5 |  |  |  |  | 9
2. Soya |  |  |  |  | 6 |  |  |  |  | 10
3. maize glutten |  |  |  |  | 7 |  |  |  |  | 11
4. MBM |  |  |  |  | 8 |  |  |  |  | 12
Type |  |  | Broiler Only |  |  |  |  | Purpose |  | Commercial sale Personal Use
Any Constraints in project - ( Land , Water level , rocky soil , height , govt. policies , power etc. )
Obsesrvations in Similar Plants:
Suggestions/ modifications required - ( approval pending ) - Discuss with jasbir ji / satbir ji
1 | 8 Batching bins - 1 =20 mt . 2 -12 mt , 2 - 10 mt, 3-6 mt 8-10 tph pellet with 8 silos
2 | Provision For Lift structure to be taken
3
Immediate actions to start with :
Any special requirements : like extra chain conveyor , elevator ,other machines etc. --
Prepared By |  | Date | Chkd By |  | Date | Approved By |  | Date |  | Received By |  |  | Date
INTAKE SECTION
1 | INTAKE CHAIN CONVEYOR - |  |  |  | Remarks - need to be check ( inclination for future expansion ) | [11 empty] | DRW. NO.
| Model | No. Of Conveyors |  |  | Length | Power | RPM | Gear Box |  | RPM | Recent Modifications done
| CC-65 | 1 |  |  | 119 ft. | 10 H.P. | 1440 | AS 60D P 33.4 P132 B5 LO + 10HP ABB Motor |  | 43 | Modifications required - over load sensors
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
2 | DUMPING HOPPER |  | Remarks - | [13 empty] | DRW. NO.
| Model |  | Recent Modifications done-
| DH-1 |  | Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
3 | JUTE REMOVER- Yes / No ----------( YES ) | [7 empty] | Remarks - | [7 empty] | DRW. NO.
| Model | Extra Rotor |  | Power | RPM | GEAR BOX |  | RPM | Recent Modifications done -
| JR SS | 1 |  | 2 H.P. | 1440 | AS30P 12.62 P90 B5B3 + BN90 L2 IP 55 |  | 112 | Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
4 | INTAKE ELEVATOR | [5 empty] | Remarks - | [9 empty] | DRW. NO.
| Model | Height | Power | RPM | Gear Box | RPM | Recent Modifications done-
| BE-14 |  | 7.5 | 1440 | AS 55 P20.4 P 132B5 B3 LO +7.5HP ABB Motor | 71 | Modifications required - bottom pulley stop sensor
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
5 | MAGNET SYSTEM |  |  |  | Remarks - | [11 empty] | DRW. NO.
| Model | Manual | Pneumatic |  | Recent Modifications done -
| LMS 14 | Manual |  |  | Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
6 | ROTARY DISTRIBUTOR | [5 empty] | Remarks - | [9 empty] | DRW. NO.
| Model |  | Power | RPM | Gear Box | RPM | Recent Modifications done -
| RD 8 |  | 0.5 | 1440 | AS 30DP 73.3 P 70 B5 B3 + BN 71 B4 IP55 | 19.1 | Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
7 | BATCHING BINS | [15 empty] | DRW. NO.
|  | Total |  | Capacity of each bin | [10 empty] | Remarks -
| No. of Bins | Capacity | Bins | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | Recent Modifications done
| 8 | 82 MT | capty. | 20 | 12 | 12 | 10 | 10 | 6 | 6 | 6 |  |  |  | Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
8 | GATES BELOW BINS |  |  | Capacity of each bin 5: Remarks - | [5 empty] | DRW. NO.
| Model | NO. | Model | Capacity of each bin 1: NO.; Capacity of each bin 2: Manual; Capacity of each bin 3: Pneumatic; Capacity of each bin 5: Recent Modifications done -
| 280X250 | 3 | 455X305 | Capacity of each bin 1: 5; Capacity of each bin 2: Manual; Capacity of each bin 5: Modifications required - handles - causing trouble in operation ( space constraint )
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
9 | FEEDER BELOW BINS |  |  | Capacity of each bin 6: Remarks - 2-Gravity feeder, 6 - screw feeder | [5 empty] | DRW. NO.
| Gravity Feeder | Model | Screw Feeder | Model | Power | RPM | Gear Box | RPM | Recent Modifications done -
| 3 | LDF 1144 | 5 |  | 5 x 5 no.s | 1440 | AS 35 P 15.37 P 112B5 B3 + BN 112 LA4 | 90 | Modifications required - gravity feeder big size / VFD setting for fine /coarse
10 | ROUND TO RECTANGLE |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | No.s |  | Capacity of each bin 2: Recent Modifications done
Modifications required - Finishing
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
11 | FLEXIBLE JOINTS |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | No.s | Model | Capacity of each bin 1: No.s; Capacity of each bin 2: Recent Modifications done
| FJ1 | 1 | FJ2 | Capacity of each bin 1: 4; Capacity of each bin 2: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
12 | WEIGH HOPPER |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | No.s | Capacity each | Capacity of each bin 2: Recent Modifications done - New Design for higher capacity
| WH-1000 | 1 | 1000 kgs | Capacity of each bin 2: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
13 | PNEUMATIC SLIDE GATE BELOW WEIGH HOPPER |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | No.s |  | Capacity of each bin 3: Recent Modifications done -
| PSG 380X400 | 1 |  | Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
14 | FLEXIBLE JOINT |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | No.s |  | Capacity of each bin 2: Recent Modifications done
| FJ3 | 1 |  | Capacity of each bin 2: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
15 | DUMP HOPPER BELOW WEIGH BIN |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | No.s | Capacity each | Capacity of each bin 2: Recent Modifications done -
| DH-1000 | 1 | 1000 kgs | Capacity of each bin 2: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
16 | BATCH CHAIN CONVEYOR - |  |  | Capacity of each bin 3: Remarks - With over load control mechanism | [5 empty] | DRW. NO.
| Model | Power | RPM | Capacity of each bin 1: Gear Box; Capacity of each bin 2: RPM; Capacity of each bin 3: Recent Modifications done - Motor & gearbox change
| CC-65 | 5 H.P. | 1440 | Capacity of each bin 1: AS 45 DP 31.1 P112 B5 (LO)+ BN 112M4 IP55; Capacity of each bin 2: 43; Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
GRINDING SECTION
17 | DUST COLLECTOR |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | Make | Power | Capacity of each bin 1: RPM; Capacity of each bin 2: Location; Capacity of each bin 3: Recent Modifications done - change in location ( grinder elevator instead of intake elevator )
| MBES/01/C-MPJF/02/SU-3 | Maxtech | 2 | Capacity of each bin 1: 1440; Capacity of each bin 2: as per drw.; Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
18 | DUMPING HOPPER |  |  | Capacity of each bin 1: Remarks - | [5 empty] | DRW. NO.
| Model |  |  | Capacity of each bin 1: Recent Modifications done -
| DH-1 |  |  | Capacity of each bin 1: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
19 | GRINDER ELEVETOR |  |  | Capacity of each bin 4: Remarks - pls varify gearbox | [5 empty] | DRW. NO.
| Model | Height | Power | Capacity of each bin 1: RPM; Capacity of each bin 2: Gear Box; Capacity of each bin 3: RPM; Capacity of each bin 4: Recent Modifications done -
| BE-14 |  | 7.5 | Capacity of each bin 1: 1440; Capacity of each bin 2: AS 55 P20.4 P 132B5 B3 LO +7.5HP ABB Motor; Capacity of each bin 4: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
20 | TWO WAY FOR BIN DISCHARGE |  |  | Capacity of each bin 1: Remarks - location as per ease in operation ( wall etc. ) | [5 empty] | DRW. NO.
| Model | Type |  | Capacity of each bin 1: Recent Modifications done - side by side type design.
| TW-GEM | Manual |  | Capacity of each bin 1: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
21 | MAGNET SYSTEM |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | Manual | Pneumatic | Capacity of each bin 2: Recent Modifications done -
| LMS 14 | Manual |  | Capacity of each bin 2: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
22 | INTERMEDIATE BIN |  | Remarks - | [13 empty] | DRW. NO.
| Model | Capacity | Recent Modifications done - sensors location
| IB 10 | 1000 kg | Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
23 | ROTARY VANE FEEDER WITH MAGNET PLATE |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | Power | RPM | Capacity of each bin 1: Gear Box; Capacity of each bin 2: RPM; Capacity of each bin 3: Recent Modifications done - Pockects / Feeder Flap / Gear Ratio /VFD Setting - For Increasing Capacity
|  | 2 H.P. | 1440 | Capacity of each bin 1: AS 35P 36.82P 90B5 B3 + BN90 LA4 IP55; Capacity of each bin 2: 38; Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
24 | FLEXIBLE JOINT |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | No.s |  | Capacity of each bin 2: Recent Modifications done
|  | 1 |  | Capacity of each bin 2: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
25 | HAMMER MILL |  |  | Capacity of each bin 6: Remarks - WITHOUT BRAKE | [5 empty] | DRW. NO.
| Model | Aspiration System |  | Capacity of each bin 2: Power; Capacity of each bin 3: RPM; Capacity of each bin 4: Setting; Capacity of each bin 6: Recent Modifications done -
| QGA 50-120 | NO |  | Capacity of each bin 2: 150; Capacity of each bin 3: 2880; Capacity of each bin 4: Fine; Capacity of each bin 6: Modifications required -
| Spares included- |  | Hammer | Capacity of each bin 2: 3.17 screen; Capacity of each bin 5: Extra Spares; Capacity of each bin 8: Hammer |  | 3.17 screen |  | 3.96 | 10.28
|  |  | 1 set | Capacity of each bin 2: 1 set; Capacity of each bin 8: Nil |  | 1 set |  | 1 set | 1 set
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
MIXING SECTION
26 | EXTRA DUMPING HOPPER |  |  | Capacity of each bin 1: Remarks - | [5 empty] | DRW. NO.
| Model |  |  | Capacity of each bin 1: Recent Modifications done -
Modifications required - cover opening ( hinderance with elevator /hook for hanging cover
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
27 | MIXER ELEVATOR |  |  | Capacity of each bin 4: Remarks - | [5 empty] | DRW. NO.
| Model | Height | Power | Capacity of each bin 1: RPM; Capacity of each bin 2: Gear Box; Capacity of each bin 3: RPM; Capacity of each bin 4: Recent Modifications done -
| BE-12 |  | 5 | Capacity of each bin 1: 1440; Capacity of each bin 2: AS 45P 15.83 P115 B5 B3LO+ BN112 M4 IP LO; Capacity of each bin 3: 88; Capacity of each bin 4: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
28 | BATCH BIN |  | Remarks - | [13 empty] | DRW. NO.
| Model | Capacity | Recent Modifications done -
| BB 10 | 1000 kg | Modifications required - corrosion at cones ( ss 304 or increased thickness )
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
29 | PNEUMATIC SLIDE GATE -BATCH BIN BB 10 |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | No.s |  | Capacity of each bin 3: Recent Modifications done -
| 380 X400 | 1 |  | Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
30 | FLEXIBLE JOINT MIXER -BATCH BIN |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | No.s |  | Capacity of each bin 2: Recent Modifications done
|  | 1 |  | Capacity of each bin 2: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
31 | MEDICINE HOPPER ON MIXER |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | Manual | Pneumatic | Capacity of each bin 2: Capacity; Capacity of each bin 3: Recent Modifications done -
| LDF-1194 | Pneumatic |  | Capacity of each bin 2: 70 Kgs; Capacity of each bin 3: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
32 | PNEUMATIC SLIDE GATE FOR MEDICINE HOPPER- |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | No.s |  | Capacity of each bin 3: Recent Modifications done -
| PSG 326X300 | 1 |  | Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
33 | FEED MIXER |  |  | Capacity of each bin 4: Remarks - location of gearbox , FRl etc. | [5 empty] | DRW. NO.
| Model - | Power | RPM | Capacity of each bin 1: Discharge gate; Capacity of each bin 3: Gearbox; Capacity of each bin 4: Recent Modifications done -
| LHMR-10 | 15 H.P. | 1440 | Capacity of each bin 1: Pneumatic; Capacity of each bin 3: GB-10; Capacity of each bin 4: Modifications required :service window location towards pellet mill
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
34 | SURGE BIN |  | Remarks - | [13 empty] | DRW. NO.
| Model | Capacity | Recent Modifications done -
|  | 1500 kg | Modifications required :Cones / sheet thickness / Location of sensors
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
PELLEING SECTION
35 | PADDLE CONVEYOR |  |  | Capacity of each bin 3: Remarks - wide discharge - jamming ( observation in sheetal feeds ) | [5 empty] | DRW. NO.
| Model | Power | RPM | Capacity of each bin 1: Gear Box; Capacity of each bin 2: RPM; Capacity of each bin 3: Recent Modifications done - RPM / sprockets - for higher capacity ( as in sheetal feeds )
| PC-10 | 5 H.P. | 1440 | Capacity of each bin 1: AS 45P15.83 P 112 B5B3 LO + BN112 M4 IP LO; Capacity of each bin 2: 88; Capacity of each bin 3: Modifications required -2 set of sprockets - must be sent )
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
36 | DUMPING HOPPER FOR RECYCLING FINES |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model |  |  | Capacity of each bin 3: Recent Modifications done -
| LDF-1199 |  |  | Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
37 | PELLET ELEVATOR |  |  | Capacity of each bin 4: Remarks - | [5 empty] | DRW. NO.
| Model | Height | Power | Capacity of each bin 1: RPM; Capacity of each bin 2: Gear Box; Capacity of each bin 3: RPM; Capacity of each bin 4: Recent Modifications done -
| BE-12 |  | 5 | Capacity of each bin 1: 1440; Capacity of each bin 2: AS 45P 15.83 P112 B5 B3LO+ BN112 M4 IP LO; Capacity of each bin 3: 88; Capacity of each bin 4: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
38 | TWO WAY FOR MASH |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | Manual | Pneumatic | Capacity of each bin 2: Recent Modifications done -
| TW-PEP | Pneumatic |  | Capacity of each bin 2: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
39 | PELLET BIN |  | Remarks | [13 empty] | DRW. NO.
| Model | Capacity | Recent Modifications done -
| PB-3 | 3000 kg | Modifications required - cones
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
40 | SLIDE GATE |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | No.s | Manual | Capacity of each bin 1: Pneumatic; Capacity of each bin 3: Recent Modifications done -
| 356 X 525 | 1 | Manual | Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
41 | SS SCREW FEEDER |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | Power | RPM | Capacity of each bin 1: GEAR BOX; Capacity of each bin 2: RPM; Capacity of each bin 3: Recent Modifications done - Sprocket / teeth ratio - For higher capacity
| SSF-600 | 3 H.P. | 1440 | Capacity of each bin 1: AS35 P 32.8 P100 B5 B3 + BN 100 LA4 IP 55; Capacity of each bin 2: 43; Capacity of each bin 3: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
42 | CONDITIONER |  |  | Capacity of each bin 4: Remarks - multi fuel injection | [5 empty] | DRW. NO.
| Model | No. | Power | Capacity of each bin 1: RPM; Capacity of each bin 2: GEAR BOX; Capacity of each bin 3: RPM; Capacity of each bin 4: Recent Modifications done -
| PC-2500 | 3 | 5 H.P. | Capacity of each bin 1: 1440; Capacity of each bin 2: AS 35 P7.5 IP112 B5 B3 + BN112 M4 IP55; Capacity of each bin 3: 191; Capacity of each bin 4: Modifications required - window opening motor side
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
43 | PELLET MILL |  |  | Capacity of each bin 3: Lubrication; Capacity of each bin 7: Remarks - die hole size will discuss with client | [5 empty] | DRW. NO.
| Model | Power | RPM | die |  | manual | auto | Die size |  | Recent Modifications done
| LPM-520 | 220 H.P. | 960 | Capacity of each bin 1: 1; Capacity of each bin 3: Manual; Capacity of each bin 5: 520/620/222; Capacity of each bin 7: Modifications required : Taper Fit
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
Modified design to reduce die changing time upto 1 hour | bar: Capacity of each bin 1 to Capacity of each bin 2
44 | TRANSITION PIECE - PELLET MILL |  |  | Capacity of each bin 2: Remarks - ss -304 | [5 empty] | DRW. NO.
| Model | Manual | Pneumatic | Capacity of each bin 2: Recent Modifications done -
|  | Manual |  | Capacity of each bin 2: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
45 | TRANSITION PIECE - COOLER |  |  | Capacity of each bin 2: Remarks - ss 304 | [5 empty] | DRW. NO.
| Model | Manual | Pneumatic | Capacity of each bin 2: Recent Modifications done -
|  | Manual |  | Capacity of each bin 2: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
46 | AIR LOCK ( SS 304 ) |  |  | Capacity of each bin 4: Remarks - | [5 empty] | DRW. NO.
| Model | Material | Power | Capacity of each bin 1: RPM; Capacity of each bin 2: GEAR BOX; Capacity of each bin 3: RPM; Capacity of each bin 4: Recent Modifications done - Sprocket / teeth ratio
|  | SS 304 | 2 H.P. | Capacity of each bin 1: 1440; Capacity of each bin 2: AS30P 32.8 P90 B5B3 +BN 90LA4; Capacity of each bin 3: 43; Capacity of each bin 4: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
47 | COOLER |  |  | Capacity of each bin 5: Remarks - New Round Type Design | [5 empty] | DRW. NO.
| Model | Power | RPM | Capacity of each bin 1: GEAR BOX; Capacity of each bin 2: RPM; Capacity of each bin 3: Rotary Spreader; Capacity of each bin 5: Recent Modifications done -
|  | 2 H.P. | 1440 | Capacity of each bin 1: AS 35 DP 65.8 P 90 B5 B3+ BN 90 S4 IP55; Capacity of each bin 2: 23; Capacity of each bin 3: NO; Capacity of each bin 5: Modifications required - Cooler hopper finishing
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
48 | ROTARY VANE FEEDER WITH BY PASS FLAP |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | Power | RPM | Capacity of each bin 1: Gear Box; Capacity of each bin 2: RPM; Capacity of each bin 3: Recent Modifications done - Modified sprocket teeth ratio/Modification to prevent leakage of materia
|  | 2 H.P. | 1440 | Capacity of each bin 1: AS 30P 32.8P90 B5 B3 +BN 90 LA4 IP55; Capacity of each bin 2: 43; Capacity of each bin 3: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
49 | CRUMBLER |  |  | Capacity of each bin 1: Remarks - | [5 empty] | DRW. NO.
| Model | Power | RPM | Capacity of each bin 1: Recent Modifications done -
| LC 250 x 1500 | 15 H.P | 960 | Capacity of each bin 1: Modifications required - vendor change rolls IKJ Mohali - discuss with jasbir ji ( approval pending )
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
50 | CRUMBLER CHAIN CONVEYOR |  |  | Capacity of each bin 3: Remarks - | [5 empty] | DRW. NO.
| Model | Power | RPM | Capacity of each bin 1: Gear Box; Capacity of each bin 2: RPM; Capacity of each bin 3: Recent Modifications done -
| CC-65 | 3 H.P. | 1440 | Capacity of each bin 1: AS 35P 32.8 P 90B5B3+ BN100 LA4 IP55; Capacity of each bin 2: 43; Capacity of each bin 3: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
BAGGING SECTION
51 | BAGGING ELEVATOR |  |  | Capacity of each bin 4: Remarks - | [5 empty] | DRW. NO.
| Model | Height | Power | Capacity of each bin 1: RPM; Capacity of each bin 2: Gear Box; Capacity of each bin 3: RPM; Capacity of each bin 4: Recent Modifications done -
| BE-12 |  | 5 | Capacity of each bin 1: 1440; Capacity of each bin 2: AS 45P 15.83 P112 B5 B3LO+ BN112 M4 IP LO; Capacity of each bin 3: 88; Capacity of each bin 4: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
52 | TWO WAY FOR SCREENER BYPASS |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | Manual | Pneumatic | Capacity of each bin 2: Recent Modifications done -
| TWM(SL)-04 | Manual |  | Capacity of each bin 2: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
53 | TWO WAY AT ELEVATOR OUTLET |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | Manual | Pneumatic | Capacity of each bin 2: Recent Modifications done -
| TWM(SL)-01 | Manual |  | Capacity of each bin 2: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
54 | TWO WAY ABOVE SCREENERS |  |  | Capacity of each bin 2: Remarks - | [5 empty] | DRW. NO.
| Model | Manual | Pneumatic | Capacity of each bin 2: Recent Modifications done -
| TWM(SL)-02 | Manual |  | Capacity of each bin 2: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
55 | SCREENER |  |  | Capacity of each bin 3: Remarks - New self cleaning design | [5 empty] | DRW. NO.
| Model | No. | Power | Capacity of each bin 1: RPM; Capacity of each bin 2: Type; Capacity of each bin 3: Recent Modifications done -
| VB-5 | 2 | 1 H.P. | Capacity of each bin 1: 1440; Capacity of each bin 2: Single deck; Capacity of each bin 3: Modifications required - inclination & cleaning provision
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
56 | CYCLONE |  |  | Capacity of each bin 1: Remarks - | [5 empty] | DRW. NO.
| Model | Material | Thick. | Capacity of each bin 1: Recent Modifications done -
| PC-10 | SS 304 | 3 mm | Capacity of each bin 1: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
57 | AIR LOCK ( MS ) |  |  | Capacity of each bin 4: Remarks - | [5 empty] | DRW. NO.
| Model | Material | Power | Capacity of each bin 1: RPM; Capacity of each bin 2: GEAR BOX; Capacity of each bin 3: RPM; Capacity of each bin 4: Recent Modifications done - Sprocket / teeth ratio
|  | MS | 2 H.P. | Capacity of each bin 1: 1440; Capacity of each bin 2: AS 30 P32.8 P 90 B5 B3 +BN 90 LA4 IP55; Capacity of each bin 3: 43; Capacity of each bin 4: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
58 | TWO WAY BELOW AIRLOCK |  |  | Capacity of each bin 1: Remarks - | [5 empty] | DRW. NO.
| Model | Manual | pnematic | Capacity of each bin 1: Recent Modifications done -
| TW-GEM | Manual |  | Capacity of each bin 1: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
59 | BLOWER |  |  | Capacity of each bin 1: Remarks - location of outlet pipe ( considering residential area / office etc. | [5 empty] | DRW. NO.
| Model | Power | RPM | Capacity of each bin 1: Recent Modifications done -
|  | 15 H.P. | 1440 | Capacity of each bin 1: Modifications required - new design ( more efficiency )
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
60 | CYCLONE DUCT |  |  | Capacity of each bin 3: Remarks - bends , etc. as per drawing with proper finishing | [5 empty] | DRW. NO.
| Model | Material | Thickness | Capacity of each bin 2: Dia; Capacity of each bin 3: Recent Modifications done -
|  | SS 304 | 2 mm | Capacity of each bin 2: 14"; Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
61 | TWO WAY |  |  | Capacity of each bin 1: Remarks - | [5 empty] | DRW. NO.
| Model | Type |  | Capacity of each bin 1: Recent Modifications done -
|  | Pneumatic |  | Capacity of each bin 1: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
62 | FINAL STORAGE BIN |  |  | Capacity of each bin 7: Remarks - | [5 empty] | DRW. NO.
| Model | Capacity | No. | Capacity of each bin 1: Manual Provision for bagging; Capacity of each bin 5: Vibrator; Capacity of each bin 7: Recent Modifications done -
|  | 5000 kg | 2 | Capacity of each bin 1: Yes; Capacity of each bin 7: Modifications required - capacity check
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
32 | PNEUMATIC SLIDE GATE |  |  | Capacity of each bin 3: Remarks -with pneumatic cylinder | [5 empty] | DRW. NO.
| Model | No.s |  | Capacity of each bin 3: Recent Modifications done -
| PSG 326X300 | 2 |  | Capacity of each bin 3: Modifications required -
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
63 | BAGGING ( Automatic / Manual / Direct Loading to truck ) |  |  | Capacity of each bin 4: ( automatic ) |  | Remarks - |  |  |  | DRW. NO.
| Model | Make | Capacity | Capacity of each bin 2: Bag Size; Capacity of each bin 3: Feeder Design; Capacity of each bin 5: Accuracy; Capacity of each bin 7: Initial Setting as per |  | Recent Modifications done -
|  | Techno |  | Capacity of each bin 3: Gravity; Capacity of each bin 5: 0.25%; Capacity of each bin 7: Poultry pellet |  | Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
64 | SLAT CONVEYOR |  |  | Capacity of each bin 5: Remarks - | [5 empty] | DRW. NO.
| Model | Make | Length | Capacity of each bin 2: Width; Capacity of each bin 3: Inclination; Capacity of each bin 5: Recent Modifications done -
|  | Stichwel | 5 m | Capacity of each bin 5: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
65 | STICHING MACHINE |  |  | Capacity of each bin 4: Remarks - | [5 empty] | DRW. NO.
| Model | Make | Thread | Capacity of each bin 2: No. of Needles; Capacity of each bin 4: Recent Modifications done -
|  | Stichwell | Double | Capacity of each bin 2: 5; Capacity of each bin 4: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
66 | COMPRESSOR |  |  | Capacity of each bin 8: Remarks - G.I & pneumatic line as per document no : | [5 empty] | DRW. NO.
| Model | Make | Power | Type |  | Dryer | Make | Model | FRl Unit |  | Recent Modifications done -
| TS03120 | Elgi | 5+5 | Capacity of each bin 3: Yes; Capacity of each bin 4: Elgi; Capacity of each bin 8: Modifications required
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
67 | OIL DOSING - ( Load Cell based / level based / level based with display | [10 empty] | Remarks - location of on/off switch feed pump , |  |  |  |  | DRW. NO.
| Type | tanks | capacaity | Capacity of each bin 2: Capcity ( wegh tank ); Capacity of each bin 4: Steam coil; Capacity of each bin 6: Type of oil | Recent Modifications done -
| Weight Basis | 2 | 1000 lt Each | Capacity of each bin 2: 100 lts; Capacity of each bin 4: Yes ( 1 tank ); Capacity of each bin 6: Free flowing | Modifications required : float valve /limit switch
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
68 | STEEL STRUCTURE |  |  | Capacity of each bin 1: Remarks - pit covers , space b/w elevator legs , chequered plate modifications as per document no : | [5 empty] | DRW. NO.
| Quantity | Design |  | Capacity of each bin 1: Recent Modifications done -
| 75 MT | upto truss -vertical structure |  | Capacity of each bin 1: Modifications required :
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
Provision for lift in structure | bar: Capacity of each bin 1 to Capacity of each bin 4
69 | PAINT | code |  | Smoke Grey |  | FR White |  | Orange |  | Green | Ferozi | Yellow | Black | Maroon |  | ANY OTHER | DRW. NO.
Quantity
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
70 | ELECTRICAL
MCC panel as per drawing no :
| Make of components as per document no: | 0.5 – 2.5 mm will be copper conducting --
| Cable - | 50 – 95 mm will be Aluminium Conducting -- |  | Capacity of each bin 4: lapp; Capacity of each bin 7: from MCC To Individual motor
havels , polycab
| Location of panel - as per drawing no : |  |  | Capacity of each bin 6: (max 6 metres distance from project)
Earthing ( client scope ) requirement as per document no :
cable routing & numbering ( for tracing ) - as per document no :
Remarks
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO:
71 | AUTOMATION |  | No. of bins 8 | [10 empty] | Remarks ( TECHNOWEIGH )
| Silo Sensors ( Make ADI ) & Cooler sensor as per document no : | [12 empty] | Location / conduit pipes
Load cells as per document no :
Limit switch as per document no :
Mimic as per drawing no:
Make of components as per document no:
| interlocking scheme as per document no: | [12 empty] | batching sequence - first for fibrous material
PLC - Allen bradley
| VFD for Batching screw feeder , Hammer mill , pellet screw , crumbler ( Make ABB ) - as per document no : | [12 empty] | vfd setting as per document no :
Temperature gauges as per :
Desktop , printer , ups - ( specifications )
MIS reporting sytem | bar: Capacity of each bin 1 to Capacity of each bin 3
Finish bag counting feedback
cable routing & numbering ( for tracing -pneumatic line ) - as per drawing no:
Over load control of conveyor and elevators
Plant performance analyzer module
Optimum Life of parts-Wearing Indication
Inventary Management, flow sequence indication at warehouse
Sensor acknowledgement at, manual dumping point
Material consumptions report, breakdown reports, finish bags
Counts, Separate energy consumption section wise
REMARKS FOR DIFFEERENT DRAWINGS AND FILE NO: